## Tasks
Resource Group | Resource Name | Task_Name1 | Task_Name2 | Task_Name3 | Duration | Start | Finish | Cost
Staff | Project Manager | Planning & Research | Develop Requirements Documentation |  | 1 day | 2011-04-04 09:00 | 2011-04-04 17:00 | 560
Staff | Project Manager | Planning & Research | Fit-Out Consultant Research |  | 0.5 days | 2011-04-05 09:00 | 2011-04-05 12:30 | 280
Staff | Project Manager | Planning & Research | Telecommunications Consultant Research |  | 0.5 days | 2011-04-05 12:30 | 2011-04-05 17:00 | 280
Staff | Project Manager | Planning & Research | IT Network Contractor Research |  | 0.5 days | 2011-04-06 09:00 | 2011-04-06 12:30 | 280
Staff | Project Manager | Planning & Research | Building Contractors Research |  | 0.5 days | 2011-04-06 12:30 | 2011-04-06 17:00 | 280
Staff | Project Manager | Planning & Research | Submit Requirements to Resources & Request Quotes |  | 2 hrs | 2011-04-07 09:00 | 2011-04-07 11:00 | 160
Staff | Project Manager | Planning & Research | Quotes Received |  | 1 hr | 2011-04-14 11:00 | 2011-04-14 12:00 | 80
|  | Planning & Research | Planning & Research Complete |  | 0 days | 2011-04-14 12:00 | 2011-04-14 12:00 | 0
Staff | Project Manager | Management Approval | Consolidate Quotes and develop proposal |  | 1.5 days | 2011-04-14 12:00 | 2011-04-15 16:30 | 840
Staff | Project Manager | Management Approval | Develop Project Plan & Durations |  | 1 hr | 2011-04-15 16:30 | 2011-04-18 09:30 | 80
Staff | Project Manager | Management Approval | Submit Project Plan & Costs to Management |  | 1 hr | 2011-04-18 09:30 | 2011-04-18 10:30 | 80
Staff | Management | Management Approval | Submit Project Plan & Costs to Management |  | 1 hr | 2011-04-18 09:30 | 2011-04-18 10:30 | 100
|  | Management Approval | Management Approval Received |  | 0 days | 2011-04-18 10:30 | 2011-04-18 10:30 | 0
Staff | Project Manager | Refit Office | Appoint Resources |  | 2 hrs | 2011-04-18 10:30 | 2011-04-18 12:30 | 160
Staff | Project Manager | Refit Office | Staff Briefing |  | 1 hr | 2011-04-18 12:30 | 2011-04-18 14:30 | 80
Staff | Staff | Refit Office | Staff Briefing |  | 1 hr | 2011-04-18 12:30 | 2011-04-18 14:30 | 350
Consultant | Fit-out Consultant | Refit Office | Fit-Out Consultations | Office Space / Structure Plan | 0.5 days | 2011-04-18 14:30 | 2011-04-19 10:00 | 277.5
Staff | Project Manager | Refit Office | Fit-Out Consultations | Office Space / Structure Plan | 0.5 days | 2011-04-18 14:30 | 2011-04-19 10:00 | 280
Consultant | Fit-out Consultant | Refit Office | Fit-Out Consultations | Select & Order Carpet | 1 hr | 2011-04-19 10:00 | 2011-04-19 11:00 | 115
Staff | Project Manager | Refit Office | Fit-Out Consultations | Select & Order Carpet | 1 hr | 2011-04-19 10:00 | 2011-04-19 11:00 | 80
Consultant | Fit-out Consultant | Refit Office | Fit-Out Consultations | Select & Order Paint | 1 hr | 2011-04-19 11:00 | 2011-04-19 12:00 | 115
Staff | Project Manager | Refit Office | Fit-Out Consultations | Select & Order Paint | 1 hr | 2011-04-19 11:00 | 2011-04-19 12:00 | 80
Consultant | Fit-out Consultant | Refit Office | Fit-Out Consultations | Select & Order Office Furniture | 1 hr | 2011-04-19 12:00 | 2011-04-19 13:00 | 115
Staff | Project Manager | Refit Office | Fit-Out Consultations | Select & Order Office Furniture | 1 hr | 2011-04-19 12:00 | 2011-04-19 13:00 | 80
Staff | Project Manager | Refit Office | Telecommuncations Consultations | Design Telephone Access Points Map | 0.5 days | 2011-04-19 14:00 | 2011-04-20 09:30 | 280
Consultant | Telecommunications consultant | Refit Office | Telecommuncations Consultations | Design Telephone Access Points Map | 0.5 days | 2011-04-19 14:00 | 2011-04-20 09:30 | 210
Staff | Project Manager | Refit Office | Telecommuncations Consultations | Select & Order New PABX | 1 hr | 2011-04-20 09:30 | 2011-04-20 10:30 | 80
Contractor | IT Consultant | Refit Office | IT Networking Consultations | Design Network Access Points Map | 0.5 days | 2011-04-20 10:30 | 2011-04-20 15:00 | 280
Staff | Project Manager | Refit Office | IT Networking Consultations | Design Network Access Points Map | 0.5 days | 2011-04-20 10:30 | 2011-04-20 15:00 | 280
Staff | Project Manager | Refit Office | IT Networking Consultations | Select & Order New PCs | 1 hr | 2011-04-20 15:00 | 2011-04-20 16:00 | 80
Staff | Project Manager | Refit Office | IT Networking Consultations | New PCs Arrive | 1 hr | 2011-04-29 16:00 | 2011-04-29 17:00 | 80
Contractor | IT Consultant | Refit Office | IT Networking Consultations | Configure SOE on PCs | 1 day | 2011-05-03 09:00 | 2011-05-03 17:00 | 560
Contractor | Carpenter | Refit Office | Restructure Office | Erect New Walls | 7 hrs | 2011-04-20 06:00 | 2011-04-26 07:00 | 490
Contractor | Plasterer | Refit Office | Restructure Office | Gyprock, Plaster & Finish | 14 hrs | 2011-04-26 07:00 | 2011-04-30 10:00 | 490
Contractor | IT Consultant | Refit Office | Restructure Office | Install Network Points | 5 hrs | 2011-05-04 09:00 | 2011-05-04 15:00 | 400
Consultant | Telecommunications consultant | Refit Office | Restructure Office | Install Phone Connections | 0.5 days | 2011-05-04 09:00 | 2011-05-04 12:30 | 700
Material | Paint | Refit Office | Restructure Office | Re-Paint | 1 day | 2011-05-05 06:00 | 2011-05-07 08:00 | 25000
Contractor | Painter | Refit Office | Restructure Office | Re-Paint | 1 day | 2011-05-05 06:00 | 2011-05-07 08:00 | 245
Materials | Carpet | Refit Office | Restructure Office | Carpet | 1 day | 2011-05-09 06:00 | 2011-05-11 07:00 | 10000
Contractor | Carpet Contractor | Refit Office | Restructure Office | Carpet | 1 day | 2011-05-09 06:00 | 2011-05-11 07:00 | 0
Contractor | Labourer | Refit Office | Restructure Office | Install New Furniture | 1 day | 2011-05-11 07:00 | 2011-05-13 08:00 | 140
Contractor | IT Consultant | Refit Office | Restructure Office | Install New PCs | 1 day | 2011-05-13 09:00 | 2011-05-13 17:00 | 560
|  | Refit Office | Restructure Office | Refit Office Complete | 0 days | 2011-05-13 17:00 | 2011-05-13 17:00 | 0
Staff | Project Manager | Office Move | Order packing boxes |  | 1 hr | 2011-05-03 09:00 | 2011-05-03 10:00 | 88
Staff | Project Manager | Office Move | Staff Pack |  | 0.5 days | 2011-05-16 09:00 | 2011-05-16 12:30 | 308
Staff | Staff | Office Move | Staff Pack |  | 0.5 days | 2011-05-16 09:00 | 2011-05-16 12:30 | 3500
Staff | Staff | Office Move | Staff Move |  | 2 days | 2011-05-16 12:30 | 2011-05-19 07:00 | 7000
Contractor | Labourer | Office Move | Staff Move |  | 2 days | 2011-05-16 12:30 | 2011-05-19 07:00 | 140
|  | Office Move | Office Move Complete |  | 0 days | 2011-05-16 17:00 | 2011-05-16 17:00 | 0

## Task Pivottable Report
Sum of Cost
Resource Group | Resource Name | Task_Name1 | Task_Name2 | Task_Name3 | Duration | Start | Finish | Total
Consultant | Fit-out Consultant | Refit Office | Fit-Out Consultations | Office Space / Structure Plan | 0.5 days | 2011-04-18 14:30 | 2011-04-19 10:00 | 277.5
|  |  |  | Office Space / Structure Plan Total |  |  |  | 277.5
|  |  |  | Select & Order Carpet | 1 hr | 2011-04-19 10:00 | 2011-04-19 11:00 | 115
|  |  |  | Select & Order Carpet Total |  |  |  | 115
|  |  |  | Select & Order Office Furniture | 1 hr | 2011-04-19 12:00 | 2011-04-19 13:00 | 115
|  |  |  | Select & Order Office Furniture Total |  |  |  | 115
|  |  |  | Select & Order Paint | 1 hr | 2011-04-19 11:00 | 2011-04-19 12:00 | 115
|  |  |  | Select & Order Paint Total |  |  |  | 115
|  |  | Fit-Out Consultations Total |  |  |  |  | 622.5
|  | Refit Office Total | [5 empty] | 622.5
| Fit-out Consultant Total | [6 empty] | 622.5
| Telecommunications consultant | Refit Office | Restructure Office | Install Phone Connections | 0.5 days | 2011-05-04 09:00 | 2011-05-04 12:30 | 700
|  |  |  | Install Phone Connections Total |  |  |  | 700
|  |  | Restructure Office Total |  |  |  |  | 700
|  |  | Telecommuncations Consultations | Design Telephone Access Points Map | 0.5 days | 2011-04-19 14:00 | 2011-04-20 09:30 | 210
|  |  |  | Design Telephone Access Points Map Total |  |  |  | 210
|  |  | Telecommuncations Consultations Total |  |  |  |  | 210
|  | Refit Office Total | [5 empty] | 910
| Telecommunications consultant Total | [6 empty] | 910
Consultant Total | [7 empty] | 1532.5
Contractor | Carpenter | Refit Office | Restructure Office | Erect New Walls | 7 hrs | 2011-04-20 06:00 | 2011-04-26 07:00 | 490
|  |  |  | Erect New Walls Total |  |  |  | 490
|  |  | Restructure Office Total |  |  |  |  | 490
|  | Refit Office Total | [5 empty] | 490
| Carpenter Total | [6 empty] | 490
| Carpet Contractor | Refit Office | Restructure Office | Carpet | 1 day | 2011-05-09 06:00 | 2011-05-11 07:00 | 0
|  |  |  | Carpet Total |  |  |  | 0
|  |  | Restructure Office Total |  |  |  |  | 0
|  | Refit Office Total | [5 empty] | 0
| Carpet Contractor Total | [6 empty] | 0
| IT Consultant | Refit Office | IT Networking Consultations | Configure SOE on PCs | 1 day | 2011-05-03 09:00 | 2011-05-03 17:00 | 560
|  |  |  | Configure SOE on PCs Total |  |  |  | 560
|  |  |  | Design Network Access Points Map | 0.5 days | 2011-04-20 10:30 | 2011-04-20 15:00 | 280
|  |  |  | Design Network Access Points Map Total |  |  |  | 280
|  |  | IT Networking Consultations Total |  |  |  |  | 840
|  |  | Restructure Office | Install Network Points | 5 hrs | 2011-05-04 09:00 | 2011-05-04 15:00 | 400
|  |  |  | Install Network Points Total |  |  |  | 400
|  |  |  | Install New PCs | 1 day | 2011-05-13 09:00 | 2011-05-13 17:00 | 560
|  |  |  | Install New PCs Total |  |  |  | 560
|  |  | Restructure Office Total |  |  |  |  | 960
|  | Refit Office Total | [5 empty] | 1800
| IT Consultant Total | [6 empty] | 1800
| Labourer | Office Move | Staff Move | (blank) | 2 days | 2011-05-16 12:30 | 2011-05-19 07:00 | 140
|  |  |  | (blank) Total |  |  |  | 140
|  |  | Staff Move Total |  |  |  |  | 140
|  | Office Move Total | [5 empty] | 140
|  | Refit Office | Restructure Office | Install New Furniture | 1 day | 2011-05-11 07:00 | 2011-05-13 08:00 | 140
|  |  |  | Install New Furniture Total |  |  |  | 140
|  |  | Restructure Office Total |  |  |  |  | 140
|  | Refit Office Total | [5 empty] | 140
| Labourer Total | [6 empty] | 280
| Painter | Refit Office | Restructure Office | Re-Paint | 1 day | 2011-05-05 06:00 | 2011-05-07 08:00 | 245
|  |  |  | Re-Paint Total |  |  |  | 245
|  |  | Restructure Office Total |  |  |  |  | 245
|  | Refit Office Total | [5 empty] | 245
| Painter Total | [6 empty] | 245
| Plasterer | Refit Office | Restructure Office | Gyprock, Plaster & Finish | 14 hrs | 2011-04-26 07:00 | 2011-04-30 10:00 | 490
|  |  |  | Gyprock, Plaster & Finish Total |  |  |  | 490
|  |  | Restructure Office Total |  |  |  |  | 490
|  | Refit Office Total | [5 empty] | 490
| Plasterer Total | [6 empty] | 490
Contractor Total | [7 empty] | 3305
Material | Paint | Refit Office | Restructure Office | Re-Paint | 1 day | 2011-05-05 06:00 | 2011-05-07 08:00 | 25000
|  |  |  | Re-Paint Total |  |  |  | 25000
|  |  | Restructure Office Total |  |  |  |  | 25000
|  | Refit Office Total | [5 empty] | 25000
| Paint Total | [6 empty] | 25000
Material Total | [7 empty] | 25000
Materials | Carpet | Refit Office | Restructure Office | Carpet | 1 day | 2011-05-09 06:00 | 2011-05-11 07:00 | 10000
|  |  |  | Carpet Total |  |  |  | 10000
|  |  | Restructure Office Total |  |  |  |  | 10000
|  | Refit Office Total | [5 empty] | 10000
| Carpet Total | [6 empty] | 10000
Materials Total | [7 empty] | 10000
Staff | Management | Management Approval | Submit Project Plan & Costs to Management | (blank) | 1 hr | 2011-04-18 09:30 | 2011-04-18 10:30 | 100
|  |  |  | (blank) Total |  |  |  | 100
|  |  | Submit Project Plan & Costs to Management Total |  |  |  |  | 100
|  | Management Approval Total | [5 empty] | 100
| Management Total | [6 empty] | 100
| Project Manager | Management Approval | Consolidate Quotes and develop proposal | (blank) | 1.5 days | 2011-04-14 12:00 | 2011-04-15 16:30 | 840
|  |  |  | (blank) Total |  |  |  | 840
|  |  | Consolidate Quotes and develop proposal Total |  |  |  |  | 840
|  |  | Develop Project Plan & Durations | (blank) | 1 hr | 2011-04-15 16:30 | 2011-04-18 09:30 | 80
|  |  |  | (blank) Total |  |  |  | 80
|  |  | Develop Project Plan & Durations Total |  |  |  |  | 80
|  |  | Submit Project Plan & Costs to Management | (blank) | 1 hr | 2011-04-18 09:30 | 2011-04-18 10:30 | 80
|  |  |  | (blank) Total |  |  |  | 80
|  |  | Submit Project Plan & Costs to Management Total |  |  |  |  | 80
|  | Management Approval Total | [5 empty] | 1000
|  | Office Move | Order packing boxes | (blank) | 1 hr | 2011-05-03 09:00 | 2011-05-03 10:00 | 88
|  |  |  | (blank) Total |  |  |  | 88
|  |  | Order packing boxes Total |  |  |  |  | 88
|  |  | Staff Pack | (blank) | 0.5 days | 2011-05-16 09:00 | 2011-05-16 12:30 | 308
|  |  |  | (blank) Total |  |  |  | 308
|  |  | Staff Pack Total |  |  |  |  | 308
|  | Office Move Total | [5 empty] | 396
|  | Planning & Research | Building Contractors Research | (blank) | 0.5 days | 2011-04-06 12:30 | 2011-04-06 17:00 | 280
|  |  |  | (blank) Total |  |  |  | 280
|  |  | Building Contractors Research Total |  |  |  |  | 280
|  |  | Develop Requirements Documentation | (blank) | 1 day | 2011-04-04 09:00 | 2011-04-04 17:00 | 560
|  |  |  | (blank) Total |  |  |  | 560
|  |  | Develop Requirements Documentation Total |  |  |  |  | 560
|  |  | Fit-Out Consultant Research | (blank) | 0.5 days | 2011-04-05 09:00 | 2011-04-05 12:30 | 280
|  |  |  | (blank) Total |  |  |  | 280
|  |  | Fit-Out Consultant Research Total |  |  |  |  | 280
|  |  | IT Network Contractor Research | (blank) | 0.5 days | 2011-04-06 09:00 | 2011-04-06 12:30 | 280
|  |  |  | (blank) Total |  |  |  | 280
|  |  | IT Network Contractor Research Total |  |  |  |  | 280
|  |  | Quotes Received | (blank) | 1 hr | 2011-04-14 11:00 | 2011-04-14 12:00 | 80
|  |  |  | (blank) Total |  |  |  | 80
|  |  | Quotes Received Total |  |  |  |  | 80
|  |  | Submit Requirements to Resources & Request Quotes | (blank) | 2 hrs | 2011-04-07 09:00 | 2011-04-07 11:00 | 160
|  |  |  | (blank) Total |  |  |  | 160
|  |  | Submit Requirements to Resources & Request Quotes Total |  |  |  |  | 160
|  |  | Telecommunications Consultant Research | (blank) | 0.5 days | 2011-04-05 12:30 | 2011-04-05 17:00 | 280
|  |  |  | (blank) Total |  |  |  | 280
|  |  | Telecommunications Consultant Research Total |  |  |  |  | 280
|  | Planning & Research Total | [5 empty] | 1920
|  | Refit Office | Appoint Resources | (blank) | 2 hrs | 2011-04-18 10:30 | 2011-04-18 12:30 | 160
|  |  |  | (blank) Total |  |  |  | 160
|  |  | Appoint Resources Total |  |  |  |  | 160
|  |  | Fit-Out Consultations | Office Space / Structure Plan | 0.5 days | 2011-04-18 14:30 | 2011-04-19 10:00 | 280
|  |  |  | Office Space / Structure Plan Total |  |  |  | 280
|  |  |  | Select & Order Carpet | 1 hr | 2011-04-19 10:00 | 2011-04-19 11:00 | 80
|  |  |  | Select & Order Carpet Total |  |  |  | 80
|  |  |  | Select & Order Office Furniture | 1 hr | 2011-04-19 12:00 | 2011-04-19 13:00 | 80
|  |  |  | Select & Order Office Furniture Total |  |  |  | 80
|  |  |  | Select & Order Paint | 1 hr | 2011-04-19 11:00 | 2011-04-19 12:00 | 80
|  |  |  | Select & Order Paint Total |  |  |  | 80
|  |  | Fit-Out Consultations Total |  |  |  |  | 520
|  |  | IT Networking Consultations | Design Network Access Points Map | 0.5 days | 2011-04-20 10:30 | 2011-04-20 15:00 | 280
|  |  |  | Design Network Access Points Map Total |  |  |  | 280
|  |  |  | New PCs Arrive | 1 hr | 2011-04-29 16:00 | 2011-04-29 17:00 | 80
|  |  |  | New PCs Arrive Total |  |  |  | 80
|  |  |  | Select & Order New PCs | 1 hr | 2011-04-20 15:00 | 2011-04-20 16:00 | 80
|  |  |  | Select & Order New PCs Total |  |  |  | 80
|  |  | IT Networking Consultations Total |  |  |  |  | 440
|  |  | Staff Briefing | (blank) | 1 hr | 2011-04-18 12:30 | 2011-04-18 14:30 | 80
|  |  |  | (blank) Total |  |  |  | 80
|  |  | Staff Briefing Total |  |  |  |  | 80
|  |  | Telecommuncations Consultations | Design Telephone Access Points Map | 0.5 days | 2011-04-19 14:00 | 2011-04-20 09:30 | 280
|  |  |  | Design Telephone Access Points Map Total |  |  |  | 280
|  |  |  | Select & Order New PABX | 1 hr | 2011-04-20 09:30 | 2011-04-20 10:30 | 80
|  |  |  | Select & Order New PABX Total |  |  |  | 80
|  |  | Telecommuncations Consultations Total |  |  |  |  | 360
|  | Refit Office Total | [5 empty] | 1560
| Project Manager Total | [6 empty] | 4876
| Staff | Office Move | Staff Move | (blank) | 2 days | 2011-05-16 12:30 | 2011-05-19 07:00 | 7000
|  |  |  | (blank) Total |  |  |  | 7000
|  |  | Staff Move Total |  |  |  |  | 7000
|  |  | Staff Pack | (blank) | 0.5 days | 2011-05-16 09:00 | 2011-05-16 12:30 | 3500
|  |  |  | (blank) Total |  |  |  | 3500
|  |  | Staff Pack Total |  |  |  |  | 3500
|  | Office Move Total | [5 empty] | 10500
|  | Refit Office | Staff Briefing | (blank) | 1 hr | 2011-04-18 12:30 | 2011-04-18 14:30 | 350
|  |  |  | (blank) Total |  |  |  | 350
|  |  | Staff Briefing Total |  |  |  |  | 350
|  | Refit Office Total | [5 empty] | 350
| Staff Total | [6 empty] | 10850
Staff Total | [7 empty] | 15826
(blank) | (blank) | Management Approval | Management Approval Received | (blank) | 0 days | 2011-04-18 10:30 | 2011-04-18 10:30 | 0
|  |  |  | (blank) Total |  |  |  | 0
|  |  | Management Approval Received Total |  |  |  |  | 0
|  | Management Approval Total | [5 empty] | 0
|  | Office Move | Office Move Complete | (blank) | 0 days | 2011-05-16 17:00 | 2011-05-16 17:00 | 0
|  |  |  | (blank) Total |  |  |  | 0
|  |  | Office Move Complete Total |  |  |  |  | 0
|  | Office Move Total | [5 empty] | 0
|  | Planning & Research | Planning & Research Complete | (blank) | 0 days | 2011-04-14 12:00 | 2011-04-14 12:00 | 0
|  |  |  | (blank) Total |  |  |  | 0
|  |  | Planning & Research Complete Total |  |  |  |  | 0
|  | Planning & Research Total | [5 empty] | 0
|  | Refit Office | Restructure Office | Refit Office Complete | 0 days | 2011-05-13 17:00 | 2011-05-13 17:00 | 0
|  |  |  | Refit Office Complete Total |  |  |  | 0
|  |  | Restructure Office Total |  |  |  |  | 0
|  | Refit Office Total | [5 empty] | 0
| (blank) Total | [6 empty] | 0
(blank) Total | [7 empty] | 0
Grand Total | [7 empty] | 55663.5

## Resources
Resource Group | Resource Name | Scheduled_Work | Cost
Contractor | Carpenter | 14 hrs | 490
Materials | Carpet | 100 Lin Metre | 10000
Contractor | Carpet Contractor | 7 hrs | 0
Consultant | Fit-out Consultant | 6.5 hrs | 622.5
Asset | Furniture | 0 hrs | 0
Material | Gyprock | 0 Sheet | 0
Material | Plaster | 0 Bag | 0
Contractor | IT Consultant | 22.5 hrs | 1800
Contractor | Labourer | 14 hrs | 280
Staff | Management | 1 hr | 100
Asset | Network Cable & Points | 0 hrs | 0
Asset | PABX & Points | 0 hrs | 0
Material | Paint | 100 Litre | 25000
Contractor | Painter | 7 hrs | 245
Asset | Personal Computers | 0 hrs | 0
Asset | Phones | 0 hrs | 0
Contractor | Plasterer | 14 hrs | 490
Staff | Project Manager | 60.5 hrs | 4876
Staff | Staff | 217 hrs | 10850
Consultant | Telecommunications consultant | 7 hrs | 910
Staff | Admin Assistant | 0 hrs | 0

## Resource Pivottable Report
Sum of Cost
Resource Group | Resource Name | Scheduled_Work | Total
Asset | Furniture | 0 hrs | 0
| Furniture Total |  | 0
| Network Cable & Points | 0 hrs | 0
| Network Cable & Points Total |  | 0
| PABX & Points | 0 hrs | 0
| PABX & Points Total |  | 0
| Personal Computers | 0 hrs | 0
| Personal Computers Total |  | 0
| Phones | 0 hrs | 0
| Phones Total |  | 0
Asset Total |  |  | 0
Consultant | Fit-out Consultant | 6.5 hrs | 622.5
| Fit-out Consultant Total |  | 622.5
| Telecommunications consultant | 7 hrs | 910
| Telecommunications consultant Total |  | 910
Consultant Total |  |  | 1532.5
Contractor | Carpenter | 14 hrs | 490
| Carpenter Total |  | 490
| Carpet Contractor | 7 hrs | 0
| Carpet Contractor Total |  | 0
| IT Consultant | 22.5 hrs | 1800
| IT Consultant Total |  | 1800
| Labourer | 14 hrs | 280
| Labourer Total |  | 280
| Painter | 7 hrs | 245
| Painter Total |  | 245
| Plasterer | 14 hrs | 490
| Plasterer Total |  | 490
Contractor Total |  |  | 3305
Material | Gyprock | 0 Sheet | 0
| Gyprock Total |  | 0
| Paint | 100 Litre | 25000
| Paint Total |  | 25000
| Plaster | 0 Bag | 0
| Plaster Total |  | 0
Material Total |  |  | 25000
Materials | Carpet | 100 Lin Metre | 10000
| Carpet Total |  | 10000
Materials Total |  |  | 10000
Staff | Admin Assistant | 0 hrs | 0
| Admin Assistant Total |  | 0
| Management | 1 hr | 100
| Management Total |  | 100
| Project Manager | 60.5 hrs | 4876
| Project Manager Total |  | 4876
| Staff | 217 hrs | 10850
| Staff Total |  | 10850
Staff Total |  |  | 15826
Grand Total |  |  | 55663.5